## Slide 1
FAITHTECH TORONTO
AI Build Night
Wednesday 9 September 2026 · 5:00 – 9:00 PM
Stone Church · 45 Davenport Rd, Toronto
GRAB A NAME TAG
NAME IN THE RAFFLE BOWL
PIZZA AT 6:30
SNACKS AND DRINKS ARE OUT
FAITHTECH TORONTO
A JESUS REVIVAL IN AND THROUGH TECH
Notes: 5:00-5:20 - DOORS. Leave this slide up while people arrive.
Becky at the door, Jordan on photos and name tags.
Quinntyne floats and starts learning who wants to build what -- this is quiet
Discover work, and it makes the 6:05 team-forming much faster.
Snacks and drinks out from 5:00 (cooler). Raffle bowl by the door -- names in
now, drawn at 8:50.
Anyone who came at 5:00 for setup help: pair them with Javier immediately.

## Slide 2
GATHER
5:20 PM · 8 MIN
Welcome
FAITHTECH TORONTO
DEMOS 8:30 PM
“You showed up on a Wednesday night with your laptop to build something for the Kingdom. That’s admirable, it’s appreciated, and it’s seen. Thank you.”
WASHROOMS
WIFI
SNACKS TABLE
PIZZA 6:30
RAFFLE 8:50
Put your name in the bowl now. We draw at 8:50.
Notes: Quinntyne leads. 8 minutes, and hold it -- every minute here comes out of build
time. Say the quote in your own words; do not read it off the screen.
Then logistics: washrooms, wifi password (on the seat-drop card), snacks table,
pizza at 6:30, raffle names in the bowl now and drawn at 8:50.
Thank Stone Church by name here as well as at the close.

## Slide 3
GATHER
5:20 PM
Opening prayer
FAITHTECH TORONTO
DEMOS 8:30 PM
“Let the favour of the Lord our God be upon us, and establish the work of our hands upon us — yes, establish the work of our hands.”
Psalm 90:17
Notes: Quinntyne leads. Prayer bookends the night -- opening 5:20, closing 8:55.
Pray over the work and over the people it is for, not just over the evening.
Keep it short and unhurried. Nobody is timing this one.

## Slide 4
GATHER
5:22 PM
Tonight
FAITHTECH TORONTO
DEMOS 8:30 PM
By 8:30 you will have a demo video you can share.
6:40
Specs
7:20
Mocks + design
7:45
Build
8:10
Demo video
Four agent runs carry the whole night, and each is paired with something worth doing while it works — eating, teaching, praying, meeting each other.
Notes: This is the shape of the night, and it is the most useful thing to land early.
Once people understand the agent runs are the spine, they stop treating the
breaks as filler and stop watching progress bars.
Becky calls every agent kickoff out loud: 6:40, 7:20, 7:45, 8:10.
Say it plainly: the 8:30 demo start is a hard stop, not a target.

## Slide 5
DISCOVER
5:28 PM · 12 MIN
Introductions
FAITHTECH TORONTO
DEMOS 8:30 PM
40 seconds each
Your name
What you make
What’s on your heart
17 of us. We’re keeping time.
Notes: 12 minutes for ~17 people. Becky times, and is allowed to be rude about it.
Hold the line on 40 seconds. If this becomes 25 minutes the build loses a whole
agent run -- that is the actual cost, so say so if it starts to slip.
Model it: go first, and take exactly 40 seconds.

## Slide 6
DISCOVER
5:40 PM · 10 MIN
The 4D cycle
FAITHTECH TORONTO
DEMOS 8:30 PM
D
Discover See clearly
Reorient through the lens of Christ. Lament. See who it touches most.
D
Discern Choose wisely
Seek God’s wisdom, then decide: Reject, Receive, Reimagine, or Create.
D
Develop Co-create
Build in sprints, running the 5R loop on every work item.
D
Demonstrate Measure love
Redefine impact as friendship compounded by time, not speed shipped.
Notes: 10 minutes, Quinntyne. Name where tonight sits in each phase:
Discover 5:28-6:05, Discern 6:05-6:15, Develop 6:15-8:10,
Demonstrate 8:10-8:50.
The video is the artifact, the friendship is the impact.
Do not over-teach this. The five R's slide is the one they will actually use.

## Slide 7
DISCOVER
5:45 PM
The five R’s
FAITHTECH TORONTO
DEMOS 8:30 PM
The loop inside every build block. Not done until all five have happened.
1
Request
Invite the Spirit into the work
A short, honest ask.
2
Receive
Wait, and write down what comes
Capture it, unedited.
3
Review
Synthesize what emerged
Shape it into a direction.
4
Render
Build toward what you saw
Make it real. Log it.
5
Rejoice
Give thanks for what was made
Name the good it serves.
Rejoice is the one you will skip. Protect the 8:30 demos.
Notes: Quinntyne. This is the loop teams run all night, so spend your minutes here
rather than on the 4D slide.
Frame Rejoice deliberately: with agents doing the typing, teams sprint through
Request and Render and skip Receive and Rejoice entirely. That is the failure
mode of an AI build night, and it is why the demos are on the schedule.

## Slide 8
DISCOVER
5:50 PM · 4 MIN
Project one — RTR
FAITHTECH TORONTO
DEMOS 8:30 PM
Reconciliation Through Relationships
Built at July’s hackathon with rightrelationship.ca, in response to the TRC’s Calls to Action.
Registration, onboarding, and a shared learning journey
Facilitator-reviewed matching, cohort map, messaging, scheduling
Next.js 16 · React 19 · Tailwind 4 · Supabase
Runs on mock data — clone it and you are building in five minutes.
Notes: Quinntyne, 4 minutes. Keep it to what someone would need in order to decide to
join. This is the safe landing spot for anyone who arrives without an idea, and
for solo builders if turnout is light -- fold them in here rather than starting
something cold.
Have the repo URL ready to paste into Slack the moment you finish.

## Slide 9
DISCOVER
5:55 PM · 10 MIN
Project two
FAITHTECH TORONTO
DEMOS 8:30 PM
Over to you
Then the invitation, to everyone: who wants in on either project? Teams of two or three.
Notes: Guest presenter, 10 minutes, confirmed Tuesday. Hand over cleanly and get out of
the way -- then hold him to 10 minutes.
Ask him to end by naming the help he actually wants, not just the idea.
Then open the invitation to the room: RTR, this project, or your own.
CONTINGENCY: if the pitch runs long, cut the 7:20 networking break to 10 minutes.
Never cut dinner and never cut the demos.

## Slide 10
DISCERN
6:05 PM · 10 MIN
Lament, then discern
FAITHTECH TORONTO
DEMOS 8:30 PM
Name what is broken, and who it hurts — before you name a feature.
Reject
Should not exist
Receive
Use it as it is
Reimagine
Redeem what is
Create
Make it new
Most ideas tonight are Reimagine or Receive — not Create.
Notes: Quinntyne leads, Javier works the room. 10 minutes.
Run the discernment call on each idea OUT LOUD -- it teaches the framework far
better than the slide does, and it kills the unbuildable ideas kindly.
Lament first. Do not let anyone jump to a feature list before they have named
who the problem hurts.
Javier: start forming teams of 2-3 while this is happening.

## Slide 11
DISCERN
6:10 PM
Scope down
FAITHTECH TORONTO
DEMOS 8:30 PM
“If it can’t be shown in a 90-second video by 8:30, it’s too big. Cut it again.”
Teams of two or three.
Write your build in one sentence on the table tent.
Notes: This is the highest-leverage sentence of the night. Say it twice.
Javier and Quinntyne go table to table and cut scope out loud -- teams will not
cut hard enough on their own, and a friendly outside voice makes it painless.
One sentence on the table tent, visible all night. If a team cannot write the
sentence, the scope is still too big.
Anyone still solo at 6:25 gets paired with a team that is already moving.

## Slide 12
DEVELOP
6:15 PM · 15 MIN
Setup sprint
FAITHTECH TORONTO
DEMOS 8:30 PM
1
Create the GitHub repo — prove push access now
2
Install the MCP servers your project needs
3
Confirm the agent-toolkit plugin loaded
4
Generate your agent instruction files
/agent-toolkit:agent-instruction-files <your project>
# it will ask: web or cli — know your answer
Notes: 15 minutes, everyone at once. Javier and Quinntyne work the room.
Produces AGENTS.md plus CLAUDE.md, GEMINI.md and copilot-instructions.
If someone did not do the pre-flight install:
claude plugin marketplace add QuinntyneBrown/agent-toolkit
claude plugin install agent-toolkit@agent-toolkit
The silent killers are Python 3.10+ on PATH, and Java + PlantUML. A team
discovers the missing PlantUML at 7:20 when the diagrams will not render.
Check both now, not later.
Anyone still stuck at 6:25 pairs up with a team that is not. Say out loud now
that a team which finishes early goes and helps a stuck team -- said in advance
it feels expected rather than like charity.

## Slide 13
DEVELOP
6:30 PM · 10 MIN
Write the mini-PRD
FAITHTECH TORONTO
DEMOS 8:30 PM
One page of prose. Ten minutes. This is the seed for everything downstream.
Who it is for
The problem
What “working” looks like
Hard stop at 6:40. It goes to the agent whether it is pretty or not.
Notes: 10 minutes. Teams write; do not let them start coding.
Prose, not bullet points -- the requirements skill does better with prose.
Hold 6:40 absolutely. An ugly PRD that reaches the agent at 6:40 beats a polished
one at 6:55, because dinner is the agent's window and the window does not move.
Becky calls the 6:40 kickoff.

## Slide 14
DEVELOP
6:40 PM
FAITHTECH TORONTO
DEMOS 8:30 PM
AGENT RUN 1
Build the specs
/agent-toolkit:requirements-engineer
<paste your mini-PRD>
→ docs/specs/L1.md + L2.md
L1 capabilities, L2 behaviours with Given/When/Then. Every L2 traces to an L1.
Notes: Becky calls this out loud. Every team starts the run before they touch food.
The agent writes L1 and L2 through the whole dinner block -- that is the design.
Do not let anyone sit and watch it. Get them to the pizza.

## Slide 15
DEVELOP
6:40 PM · 30 MIN
Pizza, and four ideas
FAITHTECH TORONTO
DEMOS 8:30 PM
Eat properly. This is the one real break of the night.
MCP
How your agent reaches tools it did not ship with.
AGENTS.md
Durable memory. Written once, read every run.
Skills
A reusable procedure you hand your agent.
Agentic workflows
Agents that run on the repo, not your laptop.
Your agents are writing L1 and L2 this entire time.
Notes: ~12 minutes standing up, over the food. No slides beyond this one -- talk.
Becky on food; pizza was ordered at 5:45 for 6:30 delivery.
Then take questions until 7:10. Do not fill the whole block with teaching --
people need to eat and the room needs to breathe.
Budget: $65 across ~17 people is about $3.80 a head. A top-up of $30-40 is
expected -- keep the receipt for FaithTech.

## Slide 16
DEVELOP
7:10 PM · 10 MIN
Read what the agent wrote
FAITHTECH TORONTO
DEMOS 8:30 PM
Receive → Review
Wrong requirements compound into wrong code faster than you can catch them.
Then write your mock prompt — and say this in it, explicitly:
HTML mocks are design artifacts, not production code. No ATDD, no tests, throwaway.
Notes: 10 minutes, teams. This is the Review step of the five R's, and it is the one
teams skip when the agent is fast.
Make them actually open L1.md and L2.md and read them. Ask one team to read a
requirement out loud -- it usually surfaces a wrong assumption immediately.
Then the mock prompt, with the design-artifact line in it. Leave that line out
and the agent will try to build the mocks properly and burn the window.
Becky calls the 7:20 kickoff.

## Slide 17
DEVELOP
7:20 PM
FAITHTECH TORONTO
DEMOS 8:30 PM
AGENT RUN 2
Mocks and detailed design
<your mock prompt>
/agent-toolkit:software-design-document
Create detailed designs from docs/specs/.
→ docs/detailed-designs/ · HTML mocks
C4, class and sequence diagrams rendered to PNG. Needs Java and PlantUML on PATH.
Notes: Becky calls it. Both things start now -- the mocks and the design documents.
The design skill REFUSES to run without L1 and L2 already in docs/specs/. It
stops and asks rather than inventing them, so a team that skipped the 6:40 run
gets caught here. Watch for it.
This is also where a missing Java/PlantUML install shows up. Fallback: they carry
on and demo the mocks plus the specs.

## Slide 18
DEVELOP
7:20 PM · 15 MIN
Stand up
FAITHTECH TORONTO
DEMOS 8:30 PM
15 minutes
Refill. Change tables.
Introduce two people who have not spoken yet.
Your agent is working. Let it.
Notes: A real break, and it is deliberate -- friendship is the point, not just the build.
Jordan: photos, and 2-3 short testimonials on camera while the room is warm.
This is the block to cut to 10 minutes if the guest pitch ran long.
Quinntyne and Javier: use it to check on the quietest team, not the loudest.

## Slide 19
DEVELOP
7:35 PM · 10 MIN
Resolve the drift
FAITHTECH TORONTO
DEMOS 8:30 PM
Your specs, designs and mocks now disagree. They always do.
Ask your agent to reconcile all three — and to report every contradiction it found.
Do this before a single line of production code exists. It is far cheaper here than at 8:15.
Notes: 10 minutes, teams. Easy to skip, expensive to skip.
Make them ask for the LIST of contradictions, not just a silent fix -- the list
is what teaches them where the drift comes from.
Becky calls the 7:45 kickoff.

## Slide 20
DEVELOP
7:45 PM
FAITHTECH TORONTO
DEMOS 8:30 PM
AGENT RUN 3
Build it — incrementally
failing acceptance test → code → green → commit
→ ATDD + Addy Osmani’s incremental implementation skill
One vertical slice at a time. No slice without an L2 behind it.
8:00 — thirty minutes left. Stop adding. Start cutting.
Notes: 25 minutes, the quietest stretch of the night.
Quinntyne and Javier float constantly. The failure mode here is a team silently
stuck for fifteen minutes -- keep circling, and ask "what is on screen right
now?" rather than "how is it going?".
Becky calls the 8:00 thirty-minute warning OUT LOUD. Any team without something
on screen by then stops adding and starts cutting.

## Slide 21
DEMONSTRATE
8:10 PM
FAITHTECH TORONTO
DEMOS 8:30 PM
AGENT RUN 4
Record the demo
/agent-toolkit:demo-video
Create a demo video for each executable application.
→ docs/demo/ · silent continuous take, 1280×720
No running code? Run it against your mocks. Everyone still leaves with a video.
Notes: Becky calls it. Every team starts the render now, then writes their words while
it runs.
Javier collects the video files on the presenting laptop by 8:25. Not 8:31.
CONTINGENCY: an agent that stalled or ate its window still demos -- the specs and
the mocks ARE a real demo, and they show the process, which is what tonight is
teaching.

## Slide 22
DEMONSTRATE
8:10 PM · 20 MIN
Write your 60 seconds
FAITHTECH TORONTO
DEMOS 8:30 PM
While the video renders. Four lines, one speaker.
1
The problem
2
Who it serves
3
What you watched the agent do
4
What is next
Video files to Javier on the presenting laptop by 8:25.
Notes: 20 minutes while the renders run. Teams write; they do not keep building.
"What you watched the agent do" is the interesting line, and the one people
forget -- it is what makes this a build night rather than a demo night.
Javier collects files by 8:25 on the presenting laptop and confirms each one
actually plays.

## Slide 23
DEMONSTRATE
8:30 PM · HARD START
Demos
FAITHTECH TORONTO
DEMOS 8:30 PM
3 minutes each — the video, then 30 seconds of words.
No live coding.
No apologies for what is not finished.
This is Rejoice. It is the fifth R, and it is on the schedule for a reason.
Notes: HARD START at 8:30. Becky holds it. ~5 teams, 3 minutes each, 20 minutes total.
Jordan records the demos.
Do not let a team apologise their way through their slot -- redirect them to what
they learned. Celebrate loudly and specifically; name what each team did that was
good. This block is the room's shared Rejoice, and it sets whether people come
back next time.

## Slide 24
SEND
8:50 PM · 5 MIN
Raffle
FAITHTECH TORONTO
Names out of the bowl.
Thank you for coming, and for building.
Notes: Becky runs the draw. Jordan gets the photo.
5 minutes -- keep it light and quick. It is a thank-you, not a segment.

## Slide 25
SEND
8:55 PM · 5 MIN
What’s next
FAITHTECH TORONTO
Keep your repo alive past tonight.
The next FaithTech Toronto date.
Thank you, Stone Church.
Closing prayer
Notes: Quinntyne. Name the next event date concretely, so people can put it in a
calendar tonight while they still feel it.
Say how to keep the repos alive: who owns each one, where it lives, what the next
commit would be.
Thank Stone Church by name. We are coming back, and the room should be left
better than they handed it to us.
Then close in prayer over the work and the people it is for.
Teardown 9:00-9:20, all hands.

## Slide 26
Build well, and rejoice.
Take your video with you. Share it.
FAITHTECH TORONTO
9 SEPTEMBER 2026 · STONE CHURCH
Notes: Leave this up through teardown.
Teardown 9:00-9:20, all hands: cooler out, garbage bagged, chairs and tables
back, lights, lock up.